## Slide 1: Mass Health APEG (Adjudicated Payment per Episode) Reimbursement Methodology
Go Live 12/31/2016

## Slide 2: Hospital Preparation Timeline
September 6, 2016
Notification from Maximus to all Acute Care Hospitals, Mass Health will replace the Payment Amount per Episode (PAPE) with the Adjudicated Payment per Episode (APEC) payment methodology for acute outpatient hospitals on December 1, 2016. All PAPE services with dates of service on or after this date will adjudicate using the new methodology. ATP and MAXFEE services are not impacted.
September 23, 2016
Mass Health completed Pilot testing during August 2016 and strongly encourages you to participate in trading partner testing beginning on September 6, 2016 through the end of October 2016.

## Slide 3: Hospital Preparation Timeline (cont.)
No changes on Remittance Advice or 837 files.
September 27, 2016
Received EDI ticket from Mass Health and an EDI analyst has been assigned.
Contact with Clearinghouse to handle submission of claim file.
Trading Partner testing to start 10/3/16. Mass Health will accept test files up 11/15/16.
Schedule a call one (1) week prior to test date.

## Slide 4: Hospital preparation (cont.)
October 4, 2016
Received test file(20) accounts with separate HSN file.
Claims chosen for testing included clinic visits, Emergency, OBS, Recurring, SDC, Extended recovery, drug infusions, high end radiology.
October 25,2016
MHA notification of Three (3) forums to prepare for initial implementation of EAPG November 1. 9, 15, 2016.
October 26, 2016
Test files in Process

## Slide 5: Hospital Preparation (cont.)
November 1, 2016 – MHA conference call
November 9, 2016 – MHA/3M on EAPG webinar
November 15, 2016 – MHA second session
November 23, 2016 – MHA notification of APEG Go-Live moved to 12/30/16.

## Slide 6: First Cliché
11/28/16 – Conference call with Maximus scheduled and postponed due to Missing Mass Health 835 files. ( 7 files total)
Ticket submitted to Clearing house on 11/23/16

## Slide 7: Hospital Preparation (cont.)
December 8, 2016 – finalized original test file of (20) claims and (10) HSN. The test remit was audit and for the most part looked ok.
We opted not to send another test file as we were satisfied with the results of the first, and time was limited by the time we reached this conclusion.

## Slide 8: Second Cliché
Added Mass health to OCE,MUE,NCCI edits due to payments being based on condition and service intensity i.e.; diagnosis/procedure. New updates effective 10/1/16
  All claims with these changes including Inpatient POA denied as Mass Health’s system was not completely updated with this update until 1/31/17 as per email from MHA.
  ICD-10: The state has fully implemented and updated its system with the current ICD-10 coding classification. Denied or incorrectly processed claims (from October 1, 2016 through the present) will be reprocessed by Mass Health over the new few weeks. If you are still seeing claims incorrectly deny of coding errors or have not seen prior denied claims reprocessed for incorrect ICD-10 coding, please let me know.

## Slide 9: APEG Billing Updates
Multiple same day visits – GO condition code usage.
Claims are processing
For Observation claims G0378 must be included in the claim submission for the 3-M grouper to properly group the episode.
The number of hours should be entered on the claim. Current coding allows a range of 8-999.
Once the claim goes through the grouper the G0378 will be assigned a unit of 1. This was an issue for us.

## Slide 10: Observation claims issues
Billing updates to the Epic system were delayed is some cases due to an issue with the build. An issue was identified in Mid January which showed some claims were still splitting after the Go-Live date.
There were 12 claims which split and 29 were sent correctly.
There was an issue with the interpretation of the Go-Live date. Was the cut off, 12/29/16 or 12/30/16? Open for discussion
Billing tip language – For Episodes spanning the APEC implementation date of 12/30, claims must be split. All services rendered prior to 12/30 must be billed following the rules of PAPE. All services rendered 12/30 and after must be billed on a separate claim using the rules of APEG.
How did you configure your system?
This issue was corrected on 1/20/17

## Slide 11: Observation issues (cont.)
The Epic system was built to post actual hours then roll up all Observation hours to a unit of one (1).
The actual billing update was that we were to include all hours in the unit FL, and the span dates on the claim, and that Mass Health would roll up the hours and process with a unit of one(1)
This was not caught on the first of only two remits received since Go-live.
Our second remit showed claims denying for #4171 “Units billed less than allowed”
Some claims did pay but we are not sure if they were paid correctly. This is currently under review and we will refile any underpaid or 0.00 paid claims.

## Slide 12: Mass health APEC claims processing
Issues relating to claims processing are as follows;
  OBS claims did not update is a timely fashion in our system. Claims splitting post 12/30/16 service dates.
  OBS claims billed with a unit of one (1) instead of # of hours.
  Modifiers PI, Q1, Q8 are denying by Mass health for invalid modifier.
  Our Technical charges are denying as overlap with our professional component claims. (small sampling)
  No cross over payments to date, only eligibility denials.

## Slide 13: Conclusion
Open Discussion